## Projekti plaan ja Gantt
Projekti plaan ja GANTT-i graafik
Projekti nimi | Projektijuht | Algus | Lõpp |  | Projekti realiseerimine, %
MES0210 Masinaelemendid-Projekt | Alex B. | 2019-02-02 | 2019-05-11 |  | 26%
Ülesande nimetus | Vastutav täitja | Algus | Lõpp | Kestus | Projekti realiseerimine | %
Projekti plaan | Alex B. | 2019-02-02 | 2019-02-03 | 1 | Täidetud | 9
Konstrueerimise lähteülesanne ja olulised nõuded | Frank C. | 2019-02-03 | 2019-02-07 | 4 | Täidetud | 9
Seadme ohutus ja CE-märk. Ohutus ja töökindlus | Jacob S. | 2019-02-07 | 2019-02-12 | 5 | Täidetud | 8
Majandustasuvus. Seadme kontseptuaalne lahend | Jacob S. | 2019-02-09 | 2019-02-11 | 2 | Tähtaeg möödas | 8
Konstrueerimine. Laagerdused | Alex B. | 2019-02-11 | 2019-02-20 | 9 | Teostamisel | 7
Konstrueerimine. Sidurid | Alex B. | 2019-02-20 | 2019-02-25 | 5 | Teostamisel | 5
Konstrueerimine. Võllide konstruktsioon ja tugevusarvutused | Frank C. | 2019-02-25 | 2019-03-05 | 8 | Mitte alustatud | 8
Konstrueerimine. Pöörlevate detailide kinnitus võllil (liistliited, pressliited jm) | Shari W. | 2019-03-05 | 2019-03-15 | 10 | Mitte alustatud | 5
Konstrueerimine. Ülekanded | Shari W. | 2019-03-15 | 2019-03-30 | 15 | Mitte alustatud | 8
Koostejoonised | Alex B. | 2019-03-30 | 2019-04-15 | 16 | Mitte alustatud | 16.5
Detailijoonised | Alex B. | 2019-04-15 | 2019-05-05 | 20 | Mitte alustatud | 16.5
Lõpp |  | 2019-05-05 | 2019-05-10 | 5 |  | 100

## Project Plan and Gantt - BLANK
PROJECT PLAN AND GANTT CHART TEMPLATE
PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS | PROJECT DELIVERABLE
SCOPE STATEMENT
TASKS | RESPONSIBLE | START | END | DAYS | STATUS
|  |  |  | 0 | Complete
|  |  |  | 0 | Complete
|  |  |  | 0 | Complete
|  |  |  | 0 | Overdue
|  |  |  | 0 | In progress
|  |  |  | 0 | In progress
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
|  |  |  | 0 | Not started
0
Right click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.

## Stakeholder List
STAKEHOLDER LIST
NAME | POSITION | ROLE IN PROJECT | EMAIL ADDRESS | REQUIREMENTS | EXPECTATIONS
John Smith | VP of Product | Final approval of milestones | john@123.com | Downtime of no longer than 20 minutes | QA to take less than 1 week, marketing to promote new features in newsletter

## Cost Baseline
COST BASELINE
ITEM / TASK | % COMPLETE | BASE COST | COST | ACTUAL COST | % BUDGET SPENT
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
COMMUNICATION PLAN
COMMUNICATION TYPE | DELIVERABLE | DESCRIPTION | DELIVERY METHOD | FREQUENCY | OWNER | AUDIENCE
Presentation | 15-minute PowerPoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team